## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Zach | Tyler | Shawn | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 0
|  | Design architecture | Project Manager | Zach, Tyler, Shawn | 6 |  |  |  | 2 | 2 | 2 | 6
| Requirements |  |  |  |  | 10 |  | 0 |  |  |  | 0
|  | Gather | Requirements Engineer | Tyler, Shawn, Zach | 3 |  |  |  | 1 | 1 | 1
|  | Analyze | Requirements Engineer | Tyler, Zach | 4 |  |  |  | 2 |  | 2 | 4
|  | Specify | Requirements Engineer | Shawn, Zach | 3 |  |  |  | 1.5 |  | 1.5 | 3
| Documentation |  |  |  |  | 18 |  | 0 |  |  |  | 0
|  | Project Outline | Project Manager | Zach | 2 | [6 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Zach, Tyler | 5 | [6 empty] | 0
|  | Project Plan | Project Manager, Developers | Tyler, Zach, Shawn | 5 | [6 empty] | 0
|  | Architecture Document | Architect | Zach, Shawn | 4 |  |  |  | 2 |  | 2 | 4
|  | Communication Planning | Developers, Requirements Engineer | Zach, Tyler, Shawn | 2 | [6 empty] | 0
0
Iteration 1: | Development |  |  |  |  | 14 |  | 0 |  |  |  | 0
|  | Determine technology needs | Researcher | Zach, Tyler, Shawn | 2 |  |  |  | 0.7 | 0.7 | 0.7 | 2.1
Establish Network for indivudual offices and corporate office |  | Determine how to set up technology to link with one another | Researcher | Zach, Tyler, Shawn | 3 |  |  |  | 1 | 1 | 1 | 3
|  | Research best environemnts (AWS, Azure) | Researcher | Tyler, zach | 3 |  |  |  | 1.5 | 1.5
|  | Research how to block certain sites for customers and other sites for employees | Researcher | Zach, Tyler | 3 |  |  |  | 1.5 | 1.5
|  | Start report/presentation | Recorder | Zach, Tyler, Shawn | 3 |  |  |  | 1 | 1 | 1
| Analysis |  |  |  |  | 4 |  | 4 |  |  |  | 0
|  | Group meeting to discuss | Team | Zach, Tyler, Shawn | 2 |  | 2 |  | 1 | 1 |  | 2
|  | Evaluate needs for next iteration | Team | Zach, Tyler, Shawn | 2 |  | 2 |  | 1 | 1 |  | 2
Iteration 2: | Development |  |  |  |  | 15 |  | 14 |  |  |  | 0
Security: Firewall, email security, web filtering. |  | Review requirements | Developers | Tyler, Zach | 3 |  | 2 |  | 1 | 1 | 0 | 2
|  | Research best systems for security | Researchers | Zach, Tyler | 4 |  | 4 |  | 2 | 2 | 0 | 4
|  | Research and discuss software found to handle email security | Researchers | Zach | 2 |  | 2 |  | 2 | 0 | 0 | 2
|  | Price technology systems for requirements | Developers | Tyler, Zach | 3 |  | 3 |  | 1.5 | 1.5 | 0 | 3
|  | Continue report/presentation | Developers | Zach, Tyler | 3 |  | 3 |  | 1 | 1 | 0 | 2
| Analysis |  |  |  |  | 4 |  | 4 |  |  |  | 0
|  | Group meeting to work and discuss | Team | Zach, Tyler | 2 |  | 2 |  | 0.7 | 0.7 | 0 | 1.4
0
|  | Evaluate needs for next iteration | Team | Tyler, Zach | 2 |  | 2 |  | 0.67 | 0.7 | 0 | 1.37
Design | [5 empty] | 0 |  | 22 |  |  |  | 0
|  | Implement any design changes | Project Manager | Zach, Tyler |  | 2 |  | 0.5 |  |  |  | 0
|  | Risk analysis | Project Manager | Zach, Tyler |  | 2 |  | 1 |  |  |  | 0
|  | Create UI design for database | Developer | Zach, Tyler |  | 10 |  | 1 | 0.5 | 1 |  | 1.5
|  | Design data structure for RSS location list | Developer | Zach, Tyler |  | 8 |  | 2 | 0.5 |  | 0 | 0.5
Development | [5 empty] | 27 |  | 0 | 0.5 |  |  | 0
Iteration 3: |  | Review requirements | Researchers | Zach, Tyler | 1 |  | 0 |  |  |  |  | 0
Database |  | research database security | Researchers | Zach, Tyler | 10 |  | 0 |  | 0.5 |  |  | 0.5
|  | research clustering and backup | Researchers | Zach, Tyler | 8 |  | 0 |  | 0.5 | 0.5 |  | 1
|  | Plan UI for database | Developer | Zach, Tyler | 8 |  | 0 |  | 1 |  |  | 1
[9 empty] | 2 |  |  | 2
| Analysis |  |  |  |  | 5 |  | 2 |  |  |  | 0
|  | Group meeting to work and discuss | Tester, Project Manager | Zach, Tyler | 3 |  | 1.5 |  |  |  |  | 0
|  | evaluate needs for next iteration | Developer | Zach, Tyler | 2 |  | 0.5 |  |  |  |  | 0
[5 empty] | 103 | 125 | 62.87 | 50.5 |  |  |  | 0
0
0
0
[9 empty] | 1 | 0.5 |  | 1.5
[9 empty] | 0.5 |  |  | 0.5
Total | [8 empty] | 32.07 | 19.6 | 11.2 | 62.87
Iteration 4: | Development |  |  |  |  | 12 |  | 14 |  |  |  | 0
PowerPoint Edit, Overall Review |  | Information Cleanup | Developers | Tyler, Zach | 3 |  | 2 |  | 1.5 | 1.5 | 0 | 3
|  | PowerPoint Edit | Developers | Zach, Tyler | 2 |  | 4 |  | 1 | 1 | 0 | 2
|  | Paperwork Clean Up | Developer | Zach | 2 |  | 2 |  | 2 | 0 | 0 | 2
|  | Presentation Preperation | Developers | Tyler, Zach | 2 |  | 3 |  | 1 | 1 | 0 | 2
|  | Continue reports | Developers | Zach, Tyler | 3 |  | 3 |  | 1.5 | 1.5 | 0 | 3
| Analysis |  |  |  |  | 4 |  | 4 |  |  |  | 0
|  | Group meeting to discuss powerpoint/presentation | Team | Zach, Tyler | 2 |  | 2 |  | 1 | 1 | 0 | 2
|  | Evaluate Paperwork | Team | Tyler, Zach | 2 |  | 2 |  | 1 | 1 | 0 | 2
[5 empty] | 183 | 218 | 0 | 119 |  |  |  | 0
Total | [8 empty] | 66.64 | 43.2 | 15.9 | 125.74