## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Zach | Tyler | Shawn | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 0
|  | Design architecture | Project Manager | Zach, Tyler, Shawn | 6 |  |  |  | 2 | 2 | 2 | 6
| Requirements |  |  |  |  | 10 |  | 0 |  |  |  | 0
|  | Gather | Requirements Engineer | Tyler, Shawn, Zach | 3 |  |  |  | 1 | 1 | 1
|  | Analyze | Requirements Engineer | Tyler, Zach | 4 |  |  |  | 2 |  | 2 | 4
|  | Specify | Requirements Engineer | Shawn, Zach | 3 |  |  |  | 1.5 |  | 1.5 | 3
| Documentation |  |  |  |  | 18 |  | 0 |  |  |  | 0
|  | Project Outline | Project Manager | Zach | 2 | [6 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Zach, Tyler | 5 | [6 empty] | 0
|  | Project Plan | Project Manager, Developers | Tyler, Zach, Shawn | 5 | [6 empty] | 0
|  | Architecture Document | Architect | Zach, Shawn | 4 |  |  |  | 2 |  | 2 | 4
|  | Communication Planning | Developers, Requirements Engineer | Zach, Tyler, Shawn | 2 | [6 empty] | 0
0
Iteration 1: | Development |  |  |  |  | 14 |  | 0 |  |  |  | 0
|  | Determine technology needs | Researcher | Zach, Tyler, Shawn | 2 |  |  |  | 0.7 | 0.7 | 0.7 | 2.1
Establish Network for indivudual offices and corporate office |  | Determine how to set up technology to link with one another | Researcher | Zach, Tyler, Shawn | 3 |  |  |  | 1 | 1 | 1 | 3
|  | Research how to secure emails and what software is the best for us to use (Anti-spam, virus detection, intrusion detection) | Researcher | Tyler, zach | 3 |  |  |  | 1.5 | 1.5
|  | Research how to block certain sites for customers and other sites for employees | Researcher | Zach, Tyler | 3 |  |  |  | 1.5 | 1.5
|  | Start report/presentation | Recorder | Zach, Tyler, Shawn | 3 |  |  |  | 1 | 1 | 1
| Analysis |  |  |  |  | 4 |  | 4 |  |  |  | 0
|  | Group meeting to discuss | Team | Zach, Tyler, Shawn | 2 |  | 2 |  | 1 | 1 |  | 2
|  | Evaluate needs for next iteration | Team | Zach, Tyler, Shawn | 2 |  | 2 |  | 1 | 1 |  | 2
Iteration 2: | Design |  |  |  |  | 12 |  | 1.5 |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  | 1
|  | Design XML format | Developer | Cuong, Kyle | 1 |  | 0 |  |  |  |  | 0
|  | Design Perl XML-handling code | Developer | Cuong, Kyle | 5 |  | 0 |  |  |  |  | 0
|  | Create UI design for balance screen | Developer | Cuong, Kyle | 2 |  | 0 |  |  |  |  | 0
| Development |  |  |  |  | 22 |  | 23 |  |  |  | 0
|  | Review requirements | Developer | Cuong, Kyle | 1 |  | 0.5 |  |  |  | 0.5 | 0.5
|  | Create XML parsing code | Developer | Cuong, Kyle | 5 |  | 3.5 |  |  |  | 3.5 | 3.5
|  | Handle XML data structure for retrieving balance | Developer | Cuong, Kyle | 10 |  | 15 |  | 3 |  | 12 | 15
|  | Implement UI | Developer | Cuong, Kyle | 4 |  | 2 |  |  |  | 2 | 2
|  | Unit Testing | Developer | Cuong, Kyle | 2 |  | 2 |  |  |  | 2 | 2
| Analysis |  |  |  |  | 6 |  | 4.5 |  |  |  | 0
|  | System Testing | Tester | Casey, David | 2 |  | 1.5 |  | 0.5 | 1 |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 2.5 |  | 0.5 |  | 2 | 2.5
|  | Evaluate needs for next iteration | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
Iteration 3: | Design |  |  |  |  | 22 |  | 4.5 |  |  |  | 0
|  | Implement any design changes | Project Manager | David, Casey | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
|  | Risk analysis | Project Manager | Casey, David | 2 |  | 1 |  | 0.5 | 0.5 |  | 1
|  | Create UI design for vendor locations | Developer | Kyle, Cuong | 10 |  | 1 |  | 1 |  |  | 1
|  | Design data structure for RSS location list | Developer | Kyle, Cuong | 8 |  | 2 |  | 2 |  |  | 2
| Development |  |  |  |  | 29 |  | 0 |  |  |  | 0
|  | Review requirements | Developer | Kyle, Cuong | 1 |  | 0 |  |  |  |  | 0
|  | Develop code for processing vendor locations | Developer | Cuong, Kyle | 10 |  | 0 |  |  |  |  | 0
|  | Implement vendor map display | Developer | Kyle, Cuong | 8 |  | 0 |  |  |  |  | 0
|  | Display vendor information | Developer | Kyle, Cuong | 8 |  | 0 |  |  |  |  | 0
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 |  |  |  |  | 0
| Analysis |  |  |  |  | 5 |  | 2 |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | David, Casey | 3 |  | 1.5 |  | 1 | 0.5 |  | 1.5
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 0.5 |  | 0.5 |  |  | 0.5
Total |  |  |  |  | 148 | 148 | 73.6 | 39.5 | 27.2 | 13.2 | 33.2 | 73.6