## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [9 empty] | Zach | Tyler | Shawn |  | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual |  | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals |  | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 6 |  | 0
|  | Design architecture | Project Manager | Zach, Tyler, Shawn | 6 |  |  |  |  | 2 | 2 | 2 |  | 6
| Requirements |  |  |  |  | 10 |  | 0 | [5 empty] | 0
|  | Gather | Requirements Engineer | Tyler, Shawn, Zach | 3 |  |  |  |  | 1 | 1 | 1
|  | Analyze | Requirements Engineer | Tyler, Zach | 4 |  |  |  |  | 2 |  | 2 |  | 4
|  | Specify | Requirements Engineer | Shawn, Zach | 3 |  |  |  |  | 1.5 |  | 1.5 |  | 3
| Documentation |  |  |  |  | 18 |  | 0 | [5 empty] | 0
|  | Project Outline | Project Manager | Zach | 2 | [8 empty] | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Zach, Tyler | 5 | [8 empty] | 0
|  | Project Plan | Project Manager, Developers | Tyler, Zach, Shawn | 5 | [8 empty] | 0
|  | Architecture Document | Architect | Zach, Shawn | 4 |  |  |  |  | 2 |  | 2 |  | 4
|  | Communication Planning | Developers, Requirements Engineer | Zach, Tyler, Shawn | 2 | [8 empty] | 0
0
Iteration 1: | Development |  |  |  |  | 14 |  | 0 | [5 empty] | 0
|  | Determine technology needs | Researcher | Zach, Tyler, Shawn | 2 |  |  |  |  | 0.7 | 0.7 | 0.7 |  | 2.1
Establish Network for indivudual offices and corporate office |  | Determine how to set up technology to link with one another | Researcher | Zach, Tyler, Shawn | 3 |  |  |  |  | 1 | 1 | 1 |  | 3
|  | Research best environemnts (AWS, Azure) | Researcher | Tyler, zach | 3 |  |  |  |  | 1.5 | 1.5
|  | Research how to block certain sites for customers and other sites for employees | Researcher | Zach, Tyler | 3 |  |  |  |  | 1.5 | 1.5
|  | Start report/presentation | Recorder | Zach, Tyler, Shawn | 3 |  |  |  |  | 1 | 1 | 1
| Analysis |  |  |  |  | 4 |  | 4 | [5 empty] | 0
|  | Group meeting to discuss | Team | Zach, Tyler, Shawn | 2 |  | 2 |  |  | 1 | 1 |  |  | 2
|  | Evaluate needs for next iteration | Team | Zach, Tyler, Shawn | 2 |  | 2 |  |  | 1 | 1 |  |  | 2
Iteration 2: | Development |  |  |  |  | 15 |  | 0 | [5 empty] | 0
Security: Firewall, email security, web filtering. |  | Review requirements | Developers | Tyler, Zach, Shawn | 3 |  |  |  |  | 1 | 1 | 1 |  | 3
|  | Research best systems for security | Researchers | Zach, Tyler | 4 |  |  |  |  | 2 | 2 | 0 |  | 4
|  | Research and discuss software found to handle email security | Researchers | Zach | 2 |  |  |  |  | 2 | 0 | 0 |  | 2
|  | Price technology systems for requirements | Developers | Tyler, Zach | 3 |  |  |  |  | 1.5 | 1.5 | 0 |  | 3
|  | Continue report/presentation | Developers | Zach, Tyler, Shawn | 3 |  |  |  |  | 1 | 1 | 1 |  | 3
| Analysis |  |  |  |  | 4 |  | 4 | [5 empty] | 0
|  | Group meeting to work and discuss | Team | Zach, Tyler, Shawn | 2 |  | 2 |  |  | 0.7 | 0.7 | 0.7 |  | 2.1
0
|  | Evaluate needs for next iteration | Team | Tyler, Zach, Shawn | 2 |  | 2 |  |  | 0.67 | 0.7 | 0.7 |  | 2.07
Design | [5 empty] | 0 |  | 0 | [5 empty] | 0
| Implement any design changes | Project Manager | David, Casey |  | 2 |  | 0.5 | [6 empty] | 0
| Risk analysis | Project Manager | Casey, David |  | 2 |  | 1 | [6 empty] | 0
| Create UI design for vendor locations | Developer | Kyle, Cuong |  | 10 |  | 1 |  |  | 0.5 | 1 |  |  | 1.5
| Design data structure for RSS location list | Developer | Kyle, Cuong |  | 8 |  | 2 |  |  | 0.5 |  | 2 |  | 2.5
Development |  |  |  |  | 29 |  | 0 |  | 0.5 |  |  |  | 0.5
Iteration 3: |  | Review requirements | Developer | Kyle, Cuong | 1 |  | 0 | [6 empty] | 0
|  | Develop code for processing vendor locations | Developer | Cuong, Kyle | 10 |  | 0 |  |  | 0.5 |  |  |  | 0.5
|  | Implement vendor map display | Developer | Kyle, Cuong | 8 |  | 0 |  |  | 0.5 | 0.5 |  |  | 1
|  | Display vendor information | Developer | Kyle, Cuong | 8 |  | 0 |  |  | 1 |  |  |  | 1
|  | Unit Testing | Developer | Kyle, Cuong | 2 |  | 0 |  |  | 2 |  |  |  | 2
| Analysis |  |  |  |  | 5 |  | 2 | [5 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | David, Casey | 3 |  | 1.5 | [6 empty] | 0
|  | Bug fix as required | Tester, Developer | David, Casey, Kyle, Cuong | 2 |  | 0.5 | [6 empty] | 0
[5 empty] | 156 | 76 | 67.77 | 10 | [5 empty] | 0
0
0
0
[10 empty] | 1 | 0.5 |  |  | 1.5
[10 empty] | 0.5 |  |  |  | 0.5
Total | [9 empty] | 31.57 | 19.6 | 16.6 |  | 67.77